## Guidance on the document
This document is the 'Action Plan' element of our Digitalisation Strategy & Action Plan. It should be reviewed in conjunction with our published strategy. The commitments in this plan link back to the strategy document for ease of reading.
The strategy will be updated every 2 years as a minimum with a 6 monthly update of progress against the plan and any additions.
The plan includes a Gantt Chart for ease of use. Planned or in progress tasks are in blue, completed are green and tasks at risk of delivery on target are in amber for transparency.
In addition to the colour coding of the Gantt chart, we also include text to inform readers of progress.
Additional tasks added through our ongoing stakeholder engagament will be highlighted as 'new' in the relevant period update.
We are committed providing stakeholders with the opportunity to share their opinions on our strategy, action plan, projects and initiatives. Any feedback and suggestions will be gratefully received and can be sent to the mailbox engagement@wwutilities.co.uk Specific enquiries requesting data or about open or previously shared data should be directed to data.requests@wwutilities.co.uk.

## The WWU Plan
We identify our stakeholders’ wants, needs, perspectives and behaviours through appropriate engagement activities analysing and reviewing feedback alongside our own and external insight to inform business decision-making and shape the delivery of the services that matter to all our stakeholders. |  |  |  | delivery behind schedule | [6 empty] | delivery on track | [6 empty] | delivery complete
Digitalisation Strategy Framework Alignment | Key Deliverable(s) | Target Benefit to Stakeholdes | Current Status | 2024 | [5 empty] | 2025 | [11 empty] | 2026
|  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Products & Services | Pathfinder | • Improved accuracy due to revised cost data (updated based on cost of living increases), additional energy demand options (e.g. H2 cars/HGVs), and live data feeds where possible • Enhanced capabilities enabling Pathfinder to run multiple scenarios simultaneously • Improved access and shareability via online-hosted platform with more user-friendly outputs | Iterative improvements to the Pathfinder platform and to Pathfinder Interactive in RIIO-GD2 and GD3 are currently being prioritised based on stakeholder feedback. More details will be made available in the next refresh of this Action Plan | 2024 Jul: Ongoing continuous improvement
| Priority Services Register (PSR) | Enable us to provide the tailered support our customers need and to share those needs with other utilities and support organisations | We currently utilise a third party system and our key role is encouraging those with specific needs and challenges to sign up. Ofgem and government are reviewing the opportunity for a centralised system in future and we are active participants in those discussions | 2024 Jul: Ongoing continuous improvement
| Digitise remaining asset data sets | Improved asset risk data ensuring investment is targeted and 'just in time'. This avoids over investment on assets | Multi occupancy building and strategic valve location and condition surveys are in progress with data being digitised in the back office. To be completed by end RIIO2 | 2024 Jul: Ongoing continuous improvement
| Open Data Sharing | Publishing data to help the wider UK make decisions on net zero and supporting consumers through the journey | Demand data and catelogue is the next data set to be followed by asset and environemtnal data sets | 2024 Jul: Ongoing continuous improvement
| Blending suite | Tools that will support hydrogen producers when considering connecting to our network | Currently working with other GDNs and key stakeholders to develop the needs case. Aim to build solutions in late 2025/early 2026 | 2024 Jul: Ongoing continuous improvement
| Consumer insight on future energy solutions in their area | Tool to enable consumers to understand their future energy options speficifc to their area | Currently working with other GDNs and key stakeholders to develop the needs case. Aim to build solutions in late 2025 to early 2026 | 2024 Jul: Ongoing continuous improvement
| Consumer Database Solution | New interoperable system to manage meter point and consumer demand data will enable real-time network management and make it easier to share data in formats and granularity required by stakeholders | Solution design completed, build to commence in January | 2024 Sep: Scoping; 2024 Oct: Initiation; 2024 Nov: Design; 2025 Jan: Build and Test; 2025 Apr: Live
Technology | Data Lakehouse | Ensures that everyone in the organisation is working with the same, up-to-date information by centralising all data into a single repository. This eliminates discrepancies and enhances decision-making accuracy. This project will not only reduces storage costs but also simplifies data management and improves data quality. With a centralised system, we can enforce consistent data processing and business logic across the organisation, making it far easier for us to meet the data sharing needs of our stakeholders. In many cases we need to apply a different set of logic for external sharing compared to internal needs for running the business. A data lakehouse will enable this which also makes it an essential tool in achieving data interoperability. | Requirements gathering ongoing | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Feb: Tender; 2025 Apr: IP; 2025 May: Initiation; 2025 Jun: Design; 2025 Jul: Build and Test; 2025 Nov: Live; 2026 Jan: Design migration to Lakehouse
| Data Analytics & Reporting Platform | Enhanced ability to derive actionable insights from our data with which to make evidence-based decisions that will improve our operational performance and enhance the value we can create for our customers and communities | Requirements gathering ongoing | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Feb: Tender; 2025 Apr: IP; 2025 May: Initiation; 2025 Jun: Design; 2025 Jul: Data; 2025 Sep: Live
| Open Data Platform | - Integrate with our Data Catalogue so that metadata can be published and shared with the various datasets. - Simplify the publication and sharing of content from our Data Asset Register to different stakeholders with discrete access permissions as required. - Provide a mechanism for users to log of data quality issues, with the ability to respond with detail how these issues were, or will be, resolved; which in turn will offer us valuable insight into who is digesting our data and how it’s being used. - Integrate workflows aligned to our enhanced digital & data governance to monitoring and fulfilment of user data requests. - Reduce manual intervention and automate where possible, reducing delays in processing data requests. - Comply with Security, Privacy and Resilience (SPaR) best practice and the WWU IT Security standards. - Improve data quality through adherence to the Dublin Core Metadata standard and enhanced metadata management; datasets published for consumption should have associated metadata captured and stored that will allow effective change management for the publication of the dataset. | Requirements gathering ongoing | 2024 Oct: Scoping; 2025 Jan: Requirements gathering; 2025 Apr: Tender; 2025 Jun: IP; 2025 Jul: Initiation; 2025 Aug: Design; 2025 Sep: Build and Test
| Data Catalogue | Transparency and awareness for data users on data held | Requirements gathering ongoing | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Feb: Tender; 2025 Apr: IP; 2025 May: Initiation; 2025 Jun: Design; 2025 Jul: Build and Test; 2025 Nov: Live
| Digital Applications | Suite of applications built in core systems to solve the problems for our data users. Will drive efficiency, saftey, better service and support decision making | Developed list of requirements and prioritised. Some built relating to exposure to vibrating tools with potential to cause long term harm | 2024 Jul: Build
| Retire legacy apps | Eliminate technical debt as obsolete applications are replaced with new digital solutions | Dependent on delivery of the digital applications project | 2025 Jul: Formally retire as replacements delivered
| Independent Data Maturity Assessment | Conducted a review of existing documentation and carried out interviews and surveying of WWU employees | Completed in Dec 2024; actions and next steps agreed | 2024 Sep: Information gathering; 2024 Nov: Analysis
People & Processes | Building in-house expertise | Competent data teams to support and deliver against the needs of data users and wider stakeholders | Some key roles filled on a temporary basis by contractors. Large recruitment programme in early 2025 | 2025 Jan: Sign off operating model, complete job descriptions advertise; 2025 Apr: Interviewing and onboarding
| Conduct a Discovery which considers how photographic or video evidence could be used to inform Health and Safety | Potential to automate critical safety alerts through visual evidence with data science applied (if appropriate) | Flight monitoring, flying the pipelines, videos are watched by experienced staff. Just beginning to trial AI and machine learning as PoC | 2024 Sep: Trial of technologies; 2025 Sep: Implementation if PoC successful
| Open Data Governance Policy Framework | Governance policies will ensure consistent and transparent data management practices across the organisation. By reducing ambiguity in roles and responsibilities, these policies will improve accountability and align WWU with regulatory frameworks, building trust with stakeholders. | Framework in final draft; stakeholder review ongoing. | 2024 Jul: Scoping and Initial Stakeholder Input; 2024 Oct: Open Policy Drafting & Open Governance Board set-up; 2025 Jan: Piloting Open Governance Framework and Board; 2025 Jul: Process Review and Refinement; 2026 Jan: Embed policy into BAU with appropriate reporting cycles
| Ownership and Accountability Model | Assigning clear roles and responsibilities for data assets will foster organisational accountability and promote proactive data management practices. By reducing operational risks and clarifying responsibilities, the model ensures better data-related decisions and strengthens the organisation’s ability to meet regulatory expectations. | Asset inventory audit underway; roles under discussion. | 2024 Jul: Inventory Audit & Role Scoping with outcomes; 2025 Jan: Defined roles aligned with new organisational structure; 2025 Jul: Pilot in critical departments; 2026 Jan: Refine and Scale to rest of organisation
| Data Quality Monitoring Framework | A data quality monitoring framework will provide real-time visibility into the accuracy, completeness, and timeliness of data, improving decision-making at all levels. By detecting and resolving data issues early, the framework reduces costs associated with poor-quality data and enhances stakeholder confidence in WWU’s data reliability. | Vendor selection in progress; requirements gathering complete. | 2024 Oct: Finalise requirements and vendor selection / onboarding; 2025 Jan: Design and Build DQ dashboards; 2025 Jul: Pilot dashboards and circulate issue logging process; 2026 Jan: Generate reporting outputs for Governance Board
| Centralised Data Catalogue | A centralised data catalogue will act as a single source of truth, enabling easier data discovery and access for internal and external stakeholders. This will reduce duplication of effort, improve collaboration, and enhance the organisation’s ability to meet data sharing and usability standards. | Initial scoping phase; metadata structure under review. | 2024 Jul: Metadata structure draft; 2024 Oct: Scoping catalogue requirements; 2025 Jan: Build catalogue & Initial User Testing; 2025 Jul: Continous Improvement; 2026 Jan: Deploy to critical departments
| Enhanced Access Control System | Strengthening access controls will ensure that data is only accessible to authorised users, reducing risks of data breaches and unauthorised access. Improved compliance with GDPR and other regulatory requirements will demonstrate WWU’s commitment to robust data handling practices, enhancing stakeholder trust. | Permissions audit completed; tool integration scoping ongoing. | 2024 Jul: Permissions Audit; 2024 Oct: Draft access policies and engage with vendor; 2025 Jan: Build and test access control tools; 2025 Jul: Go live with select systems; 2026 Jan: Generate audit logs and reporting cycles
| Validation Rules Integration | The deployment of automated validation rules will ensure that data entered into systems is accurate and complete, reducing errors at the source. By improving data reliability, these rules will support better decision-making and increase operational efficiency by reducing time spent correcting data inconsistencies. | Draft validation rules under review; system testing planned. | 2024 Oct: Develop and test validation rules in pilot workflows; 2025 Jan: Test and refine rules in broader workflows; 2025 Jul: Integrate with operational systems; 2026 Jan: Assess outcomes and optimise based on feedback
| Enriched Disaster Recovery Protocols | Disaster recovery protocols will protect critical systems and data assets, ensuring resilience during disruptions. By reducing downtime and minimising financial impacts, these protocols will enhance stakeholder trust and demonstrate WWU’s preparedness to handle unexpected incidents. | Risk assessment complete; draft recovery plan in preparation. | 2024 Jul: Risk Asessment and draft disaster recovery plan; 2025 Jan: Governance Board Review; 2025 Jul: Operational Simulations; 2026 Jan: Go live for critical systems
| Metadata Management Practices | Improved metadata standards and automated generation processes will enhance the usability and discoverability of data. By ensuring metadata is consistent, accurate, and accessible, these practices will improve data sharing, reduce time spent searching for data, and support better collaboration across teams and with stakeholders. | Metadata policy in draft; pilot projects initiated. | 2024 Oct: Draft metadata policy and engage stakeholders; 2025 Jan: Pilot metadata tools; 2025 Jul: Governance Board Review; 2026 Jan: Refine and expand across organisation